## Consultancy
PROCUREMENT PLAN
1 | General
| Organisation: | NEPAD Planning and Coordinating Agency | NEPAD Planning and Coordinating Agency
| Category | CONSULTANCY
Project/Programme Description
Project ID
Implementing Unit:
| Approval Date of Procurement Plan: | [Original: ] Revision 1:
| Period Covered by these Proc. Plans: | JAN 2019 - DEC 2019 | JAN 2019 - DEC 2019
| Approval Thresholds: | As per AU Procurement Manual
Contract Value
| Selectiont Method | Threshold |  |  | Comments
(USD)
| RFP/RFB | >100,000 |  |  | AUC-IPC Approval
| RFQ/RFB/RFP | 2,001 - 100,000 |  |  | 0-15,000 (Approval by Head of Procurement/Director/Acting Director or OIC) 15,001 - 50,000 (Approval by CEO) 50,0001 - 100,000 (Approval by IPC)
| Direct Selection/RFQ | > 2,000
| Direct Selection/RFQ | ≤2,000 |  |  | non-competitive/RFQ (Approval by Head of Procurement)
NB: all TOR regardless of the value to be approved by PMO
[6 empty] | Contract Type |  |  |  |  | Preparation Terms of Reference |  |  |  | Short List |  |  | Request for Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiations (N) | [5 empty] | Draft Contract |  | Contract Finalization | [5 empty] | Contract Implementation |  |  |  | Remarks
| Description* | Reference Number | Department | Source of Funding | Selection Method | Lumpsum or Time-Based | Estimated Amount | Actual Amount in US $ | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway/AU WebS. Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation & Approval (IPC) Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Contract Signature | PO Number | BUYER | Plan vs. Actual | Mobilization Advance Payment | Draft Report/ Commencment | Final Report | Final Cost
| Norm Duration of Proc Steps | [8 empty] | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks |  |  | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
List of Contracts
CARRIED OVER FROM 2018
1 | Procurement of Consultancy Sertvices for the Upgrading of Kalundu-Uvira-Kamanyola-Bukavu Road to Bitumen Standard |  | RIITP | PIDA CAP/CCTTFA |  | lumpsum | 400000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
2 | Procurement of Consultancy Services for the Development of Praia- Dakar-Abidjan- Lagos Corridor Investment Plan | COMESA | RIITP | AfDB PIDA CAP | QCBS | Lumpsum | 360000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
3 | EAC : Consultancy Services for the Preparation of the Corridor Investment Development Plan for the Northern Multimodal Corridor | NPCA/PIDA/QCBS/01-2017 | RIITP | AfDB/MS | QCBS | lumpsum | 95000 |  | Prior | Plan | 2017-07-01 | 2017-07-15 | 2017-07-22 | 2017-08-05 | 2017-08-19 | 2017-09-02 | Plan | 2017-09-09 | 2017-10-09 | 2017-10-30 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-11 | Plan | 2017-12-18 | 2018-01-01 | 641150 | 2018-01-08 | 2018-01-22 |  | Plan
[10 empty] | Actual |  |  | 2017-09-25 | 2017-10-20 | 2017-11-02 | 2017-11-13 | Actual | 2017-11-06 | 2018-01-17 | 2018-02-28 | 2018-03-14 | 2018-04-19 | 2018-06-25 | 2018-06-18 | Actual | 2018-07-26 | [5 empty] | Actual
4 | Consultancy services for public relations and media outreach services | NPCA/ICEO/CU/QCBS/67-2017 | OCEO | Core | QCBS | lumpsum | 90000 | 525686.98 | Prior | Plan | 2018-02-28 | 2018-03-14 | 2018-03-21 | 2018-04-04 | 2018-04-18 | 2018-05-02 | Plan | 2018-05-09 | 2018-06-08 | 2018-06-29 | 2018-07-13 | 2018-07-20 | 2018-07-27 | 2018-08-10 | Plan | 2018-08-17 | 2018-08-31 | 525686.98 | 2018-09-07 | 2018-09-21 |  | Plan
[10 empty] | Actual |  |  | 2017-08-29 | 2017-09-22 | 2017-12-07 | 2017-12-12 | Actual | 2017-12-15 | 2018-01-26 | 2018-04-18 | 2018-06-16 | 2018-09-04 | 2018-11-05 | 2018-12-20 | Actual |  | 2018-12-26 |  | 2019-01-08 |  |  | Actual
5 | Consultancy to conduct impact evaluation of the spanish fund (Gender) | 44/NPCA/OCEO/GD-BIAWE/QCBS/2018 | OCEO | Spanish Fund | QCBS | lump-sum | 106000 |  | prior | Plan | 2018-10-01 | 2018-10-15 | 2018-10-22 | 2018-11-05 | 2018-11-19 | 2018-12-03 | Plan | 2018-12-10 | 2019-01-09 | 2019-01-30 | 2019-02-13 | 2019-02-20 | 2019-02-27 | 2019-03-13 | Plan | 2019-03-20 | 2019-04-03 |  | 2019-04-10 | 2019-04-24 |  | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
6 | Consultancy for establishing help desks for administrative data compilation and inventory of satellite imagery on land in selected 8 African countries | 114/NPCA/NRG/LANDGOV/QCBS/2018 | NRG | LandGov | QCBS | lumpsum | 250000 |  | Prior | Plan | 2018-11-15 | 2018-11-29 | 2018-12-06 | 2018-12-20 | 2019-01-03 | 2019-01-17 | Plan | 2019-01-24 | 2019-02-23 | 2019-03-16 | 2019-03-30 | 2019-04-06 | 2019-04-13 | 2019-04-27 | Plan | 2019-05-04 | 2019-05-18 |  | 2019-05-25 | 2019-06-08 |  | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
7 | Consultancy for establishing help desks for administrative data compilation and inventory of satellite imagery on land in selected 4 Francophone African countries | 115/NPCA/NRG/LANDGOV/QCBS/2018 | NRG | LandGov | QCBS | lumpsum | 200000 |  | Prior | Plan | 2018-11-15 | 2018-11-29 | 2018-12-06 | 2018-12-20 | 2019-01-03 | 2019-01-17 | Plan | 2019-01-24 | 2019-02-23 | 2019-03-16 | 2019-03-30 | 2019-04-06 | 2019-04-13 | 2019-04-27 | Plan | 2019-05-04 | 2019-05-18 |  | 2019-05-25 | 2019-06-08 |  | Plan
[10 empty] | Actual |  |  | 2017-08-29 | 2017-09-22 | 2017-12-07 | 2017-12-12 | Actual | 2017-12-15 | 2018-01-26 | 2018-04-18 | 2018-06-16 | 2018-09-04 |  |  | Actual | [6 empty] | Actual
8 | Consultancy for socio-economic land data inventory | 116/NPCA/NRG/LANDGOV/QCBS/2018 | NRG | LandGov | QCBS | lumpsum | 187000 |  | Prior | Plan | 2018-11-15 | 2018-11-29 | 2018-12-06 | 2018-12-20 | 2019-01-03 | 2019-01-17 | Plan | 2019-01-24 | 2019-02-23 | 2019-03-16 | 2019-03-30 | 2019-04-06 | 2019-04-13 | 2019-04-27 | Plan | 2019-05-04 | 2019-05-18 |  | 2019-05-25 | 2019-06-08 |  | Plan
[10 empty] | Actual |  |  | 2017-08-29 | 2017-09-22 | 2017-12-07 | 2017-12-12 | Actual | 2017-12-15 | 2018-01-26 | 2018-04-18 | 2018-06-16 | 2018-09-04 |  |  | Actual | [6 empty] | Actual
9 | Consultancy services to transfer SAP HANA application platform from SAP data centre to a new data centre in Africa | 113/NPCA/BS/IT/CQS/2018 | BS | Core | CQS | Lumpsum | 60000 |  | Prior | Plan | 2018-11-07 | 2018-11-21 | 2018-11-28 | 2018-12-12 | 2018-12-26 | 2019-01-09 | Plan | 2019-01-16 | 2019-02-15 | N/A | N/A | N/A | 2019-02-22 | 2019-03-08 | Plan | 2019-03-15 | 2019-03-29 | 55000 | 2019-04-05 | 2019-04-19 |  | Plan
[10 empty] | Actual | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-21 |  |  | Actual |  | 2018-06-28 | N/A | N/A | N/A |  |  | Actual | [6 empty] | Actual
10 | Consultancy services to Conduct a Study on Opportunities for Private Sector Participation in TB control -Private Sector Health Expert | 109/NPCA/ISTI/TB/IC/2018 | ISTI | World Bank | ICS | lumpsum | 68000 | 46400 | Post | Plan | 2018-08-29 | 2018-09-05 | 2018-09-08 | 2018-09-26 |  | NA | Plan | n/a | NA | NA | N/A | N/A | N/A | 2018-10-10 | Plan | NA | NA | 46400 | 2018-10-16 | 2018-10-24 |  | Plan | NA | 2019-09-20 | 2019-10-16
[10 empty] | Actual | 2018-08-27 | 2018-08-27 | 2018-09-13 | 2018-09-28 |  |  | Actual | [6 empty] | 2018-11-27 | Actual | 2018-12-10 |  |  | 2019-01-08 | 2019-01-14 |  | Actual |  | n/a
11 | Consultancy services to Conduct a Study on Opportunities for Private Sector Participation in TB control -Public Health Expert | 110/NPCA/ISTI/TB/IC/2018 | ISTI | World Bank | ICS | lumpsum | 58000 | 35750 | Post | Plan | 2018-08-29 | 2018-09-05 | 2018-09-08 | 2018-09-26 |  | NA | Plan | n/a | NA | NA | N/A | N/A | N/A | 2018-10-10 | Plan | NA | NA | 35750 | 2018-10-16 | 2018-10-24 |  | Plan | NA | 2019-09-20 | 2019-10-16
[10 empty] | Actual | 2018-08-27 | 2018-08-27 | 2018-09-13 | 2018-09-28 |  |  | Actual | [6 empty] | 2018-11-27 | Actual | 2018-12-10 |  |  | 2019-01-08 | 2019-01-14 |  | Actual |  | n/a
NEW ACTITIVITIES FOR 2019
1 | Consultancy services to develop and edit STEM/STI training materials and resources for policy makers and education practitioners (Gabon and Malawi) | 1/NPCA/ISTI/STEM/IC/2019 | ISTI | MSC | ICS | Lumpsum | 8200 |  | Post | Plan | 2019-02-28 | [5 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
2 | Consultancy services to develop and edit STEM/STI training materials and resources for policy makers and education practitioners (Nigeria and Ghana) | 1/NPCA/ISTI/STEM/IC/2019 | ISTI | MSC | ICS | Lumpsum | 8200 |  | Post | Plan | 2019-02-28 | [5 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
3 | Recruit training institution to train Health care professionals (Nurses & Midwifery) at the Master degree's level in Cameroon |  | ISTI | China Aid | QCBS | Lumpsum | 300000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
4 | Consultancy services to edit regional guidelines for mine health and safety inspection | 4/NPCA/ISTI/TB/IC/2019 | ISTI | WB | ICS | Lumpsum | 20000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
5 | Consultancy services to edit regional training manual for mine inspectors | 5/NPCA/ISTI/TB/IC/2019 | ISTI | WB | ICS | Lumpsum | 20000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
6 | Consultancy services to draft regional policy on mine health and safety | 6/NPCA/ISTI/TB/IC/2019 | ISTI | WB | QCBS | Lumpsum | 50000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
7 | Recruit consultant to facilitate development of a training manual on dossier assessment and GMP inspection for RECs through identified RCORE |  | ISTI | BMGF | CQS | Lumpsum | 40000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
8 | Consultancy Services to develop and maintain AMRH and M&E web based portal to facilitate application process, report and work sharing; redesign and regular update of the website |  | ISTI | BMGF | SSS | Lumpsum | 37000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
9 | Commission a Consultant to support AMRH transitioning into AMA |  | ISTI | BMGF | QCBS | lump-sum | 60000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
10 | Create and launch electronic Platform for new AMRH Partnerships |  | ISTI | BMGF | SSS | lump-sum | 15000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
11 | Consultancy to facilitate annual joint regional planning and review meetings (PIC and High Level Meetings) |  | ISTI | Global Fund | ICS | Lumpsum | 15000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
12 | Counsultany services to facilitate constituency engagement for the new members of the Regional Coordinating Mechanism for the tuberculosis in the mining sector in Southern Africa project |  | ISTI | Global Fund | ICS | Lumpsum | 10000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
13 | Consultancy service to deliver RCM Capacity building and Knowledge Exchange including RCM sub-committees |  | ISTI | Global Fund | ICS | Lumpsum | 15000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
14 | ASTF: Consultancy services to conduct M&E tracer study of the project and set up a baseline of trainees for annual follow up |  | SEFY | MSC | QCBS | Lumpsum | 40000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
15 | ASTF: Consultancy to develop Curricula for 5 strategic value chains and mainstreamed into National Qualification Frameworks in Benin, Cameroon, Malawi and Niger |  | SEFY | MSC | QCBS | Lumpsum | 245000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
16 | Consultancy Services to develop a manual/toolkit on inclusivity and gender mainstream for infrastructure development & Translation |  | RIITP | MSC | ICS | Lumpsum | 24500 |  | Post | Plan | 2019-02-28 | 2019-03-07 | N/A | 2019-03-14 | 2019-03-21 | N/A | Plan | 2019-03-28 | 2019-04-04 | 2019-04-09 | N/A | N/A | 2019-04-12 | 2019-04-17 | Plan | 2019-04-22 | N/A |  | 2019-04-27 | 2019-05-01 |  |  | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
17 | Procurement of Facilitation services for the Preparation of Cybersecurity country assessments and facilitation of workshop |  | RIITP | MSC | SSS | Lumpsum | 12500 |  | Post | Plan | 2019-02-28 | [5 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
18 | Consultancy Services to Develop demand studies for the North South Corridor railway projects, Beira Corridor and the BGHP |  | RIITP | MSC | CQS | Lumpsum | 50000 |  | Prior | Plan | 2019-03-01 | N/A | 2019-03-08 | 2019-03-23 | 2019-03-28 | 2019-04-07 | Plan | 2019-04-14 | 2019-04-28 | 2019-05-08 | 2019-05-15 | 2019-05-20 | 2019-05-30 | 2019-06-06 | Plan | 2019-06-13 | 2019-06-16 |  | 2019-06-23 | 2019-06-30 |  |  | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
19 | Provision of Agribusiness Advisory Services to the Grow Africa Programme |  | NRG | ??? | ICS | Lumpsum | 60000 |  | Post | Plan | 2019-02-15 | 2019-02-18 | 2019-02-18 | N/A | 2019-03-04 | N/A | Plan | 2019-03-18 | 2019-03-23 | 2019-03-30 | N/A | N/A | 2019-04-06 | 2019-04-11 | Plan | 2019-04-18 | N/A |  | 2019-04-23 | 2019-04-30 |  |  | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
20 | Consultancy Services to develop the new AUDA branding strategy with logo, tag line and branding guidelines | 01/NPCA/OCEO/COMMS/IC/2019 | OCEO | MSC | ICS | Lumpsum | 20000 |  | Prior | Plan | 2018-02-10 | 2018-02-24 | 2018-03-03 | 2018-03-17 | 2018-03-31 | 2018-04-14 | Plan | 2018-04-21 | 2018-05-21 | 2018-06-11 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-23 | Plan | 2018-07-30 | 2018-08-13 |  | 2018-08-20 | 2018-09-03 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
21 | Consultancy Services to develop a master plan for the selection, implementation and deployment of an Enterprise Resource Planning (ERP) System for ECCAS Secretariat | 04/NPCA/OCEO/CDD/QCBS/2019 | OCEO | MSC | QCBS | Lumpsum | 100000 |  | Post | Plan | 2018-02-14 | 2018-02-28 | 2018-03-07 | 2018-03-21 | 2018-04-04 | 2018-04-18 | Plan | 2018-04-25 | 2018-05-25 | 2018-06-15 | 2018-06-29 | 2018-07-06 | 2018-07-13 | 2018-07-27 | Plan | 2018-08-03 | 2018-08-17 |  | 2018-08-24 | 2018-09-07 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
22 | Consultancy Services to develop ECCAS Secretariat's Standard Operating Procedures for Effective Delivery of the Regional Strategy and Agenda 2063 | 05/NPCA/OCEO/CDD/CQS/2019 | OCEO | MSC | CQS | Lumpsum | 20000 |  | Post | Plan | 2018-02-12 | 2018-02-26 | 2018-03-05 | 2018-03-19 | 2018-04-02 | 2018-04-16 | Plan | 2018-04-23 | 2018-05-23 | 2018-06-13 | 2018-06-27 | 2018-07-04 | 2018-07-11 | 2018-07-25 | Plan | 2018-08-01 | 2018-08-15 |  | 2018-08-22 | 2018-09-05 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
23 | Consultancy Services for Support to the Africa Region on Enhancing Country Results Frameworks (CRFs) – Coordination of In-Country CRF Activities and Preparations for Regional Engagements | 06/NPCA/OCEO/CDD/IC/2019 | OCEO | MSC | IC | Lumpsum | 10000 |  | Post | Plan | 2018-02-13 | 2018-02-27 | 2018-03-06 | 2018-03-20 | 2018-04-03 | 2018-04-17 | Plan | 2018-04-24 | 2018-05-24 | 2018-06-14 | 2018-06-28 | 2018-07-05 | 2018-07-12 | 2018-07-26 | Plan | 2018-08-02 | 2018-08-16 |  | 2018-08-23 | 2018-09-06 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
24 | Consultancy Services to develop Standard Citizen Engagement Indicators and Tools for Agenda 2063 | 07/NPCA/OCEO/CDD/IC/2019 | OCEO | MSC | IC | Lumpsum | 15000 |  | Post | Plan | 2018-02-25 | 2018-03-11 | 2018-03-18 | 2018-04-01 | 2018-04-15 | 2018-04-29 | Plan | 2018-05-06 | 2018-06-05 | 2018-06-26 | 2018-07-10 | 2018-07-17 | 2018-07-24 | 2018-08-07 | Plan | 2018-08-14 | 2018-08-28 |  | 2018-09-04 | 2018-09-18 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
25 | Consultancy services for Mapping and appraisal of existing development and policy research think tanks and knowledge organisations/initiatives with interest/focus on Africa and Africa-related issues | 00/NPCA/OCEO/PD/IC/2019 | OCEO | MSC | ICS | Lumpsum | 20000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
26 | Consultancy services to prepare intelligence analysis and briefings on evolving trends and to provide early warning signals on A2063 issues in Africa | 00/NPCA/OCEO/PD/IC/2019 | OCEO | MSC | ICS | Lumpsum | 50000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
27 | Consultancy services to conduct phase 2 of foresight studies. | 00/NPCA/OCEO/PD/IC/2019 | OCEO | MSC | SSS | Lumpsum | 25000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
28 | Consultancy services for enhancement of the AUDA-NPCA web-portal | 08/NPCA/PIS/SKM/CQS/2019 | PIO | MSC | CQS | lump-sum | 50000 |  | Prior | Plan | 2018-02-25 | 2018-03-11 | 2018-03-18 | 2018-04-01 | 2018-04-15 | 2018-04-29 | Plan | 2018-05-06 | 2018-06-05 | 2018-06-26 | 2018-07-10 | 2018-07-17 | 2018-07-24 | 2018-08-07 | Plan | 2018-08-14 | 2018-08-28 |  | 2018-09-04 | 2018-09-18 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
29 | Consultancy services to develop country level A63 and SDG database | 09/NPCA/PIS/SKM/IC/2019 | PIO | MSC | IC | lump-sum | 20000 |  | Prior | Plan | 2018-02-25 | 2018-03-11 | 2018-03-18 | 2018-04-01 | 2018-04-15 | 2018-04-29 | Plan | 2018-05-06 | 2018-06-05 | 2018-06-26 | 2018-07-10 | 2018-07-17 | 2018-07-24 | 2018-08-07 | Plan | 2018-08-14 | 2018-08-28 |  | 2018-09-04 | 2018-09-18 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
30 | Consultancy services for maintenance and hosting of the web-platform | 03/NPCA/PIS/SKM/CQS/2019 | PIO | MSC | SSS | lump-sum | 17000 |  | Prior | Plan | 2018-03-25 | 2018-04-08 | 2018-04-15 | 2018-04-29 | 2018-05-13 | 2018-05-27 | Plan | 2018-06-03 | 2018-07-03 | 2018-07-24 | 2018-08-07 | 2018-08-14 | 2018-08-21 | 2018-09-04 | Plan | 2018-09-11 | 2018-09-25 |  | 2018-10-02 | 2018-10-16 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
31 | Consultancy services for development of materials and train RECs and MS in knowledge generation, exchange and management | 10/NPCA/PIS/SKM/IC/2019 | PIO | MSC | ICS | lump-sum | 16000 |  | Prior | Plan | 2018-04-25 | 2018-05-09 | 2018-05-16 | 2018-05-30 | 2018-06-13 | 2018-06-27 | Plan | 2018-07-04 | 2018-08-03 | 2018-08-24 | 2018-09-07 | 2018-09-14 | 2018-09-21 | 2018-10-05 | Plan | 2018-10-12 | 2018-10-26 |  | 2018-11-02 | 2018-11-16 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
28 | Consultancy service for the development and maintance of NEPAD Geo-Portal |  | PIO | MSC | SSS | Lumpsum | 90000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
29 | Consultancy service for the Engagement of experts for APP development (Mobile. App, Risk management etc.) | 00/NPCA/ICT/MSC/IC/2019 | BS | MSC | ICS | lumpsum | 80000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
30 | Consultancy services to develop a web-based automated invoice receipting systems | 00/NPCA/FIN/MSC/IC/2019 | BS | MSC | ICS | lumpsum | 10000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
31 | Consultancy Services for the Finalization of NPCA Accreditation to GCF | 8/NPCA/NRG/CCR/CQS/2019 | NRG | MSC | CQS | Lumpsum | 50000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
32 | Consultancy Services to develop framework document for African Climate Change and Resilience Centre | 9/NPCA/NRG/CCR/IC/2019 | NRG | MSC | ICS | lump-sum | 60000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
32 | Consultancy Services for the Development and Maintenance of Database and Dashboard on Status of Regional Flagship Programmes | 10/NPCA/NRG/ENG/IC/2019 | NRG | MSC | ICS | lump-sum | 15000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
33 | Consultancy Services for the elaboration of 4 feasibility studies and bankable projects-Bioenergy | 10/NPCA/NRG/UEMOA/CQBS/2019 | NRG | UEMOA | QCBS | lump-sum | 200000 |  | Post | Plan | 2019-04-01 | 2019-04-15 | 2019-04-22 | 2019-05-06 | 2019-05-20 | 2019-06-03 | Plan | 2019-06-10 | 2019-07-10 | 2019-07-31 | 2019-08-14 | 2019-08-21 | 2019-08-28 | 2019-09-11 | Plan | 2019-09-18 | 2019-10-02 |  | 2019-10-09 | 2019-10-23 |  | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
34 | Consultancy Services for the Harmonisation of Policies and Regulatory frameworks and capacity strenghtening of Bioenergy | 11/NPCA/NRG/UEMOA/CQS/2019 | NRG | UEMOA | CQS | Lumpsum | 30000 |  | Post | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
35 | Consultancy Services for the knowledge products of Bioenergy | 11/NPCA/NRG/UEMOA/IC/2019 | NRG | UEMOA | ICS | Lumpsum | 20000 |  | Post | Plan | 2019-05-01 | 2019-05-15 | 2019-05-22 | 2019-06-05 | 2019-06-19 | 2019-07-03 | Plan | 2019-07-10 | 2019-08-09 | 2019-08-30 | 2019-09-13 | 2019-09-20 | 2019-09-27 | 2019-10-11 | Plan | 2019-10-18 | 2019-11-01 |  | 2019-11-08 | 2019-11-22 |  | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
36 | Procurement of Audit Services for UEMOA funds | 11/NPCA/NRG/UEMOA/LCS/2019 | NRG | UEMOA | LCS | Lumpsum | 10000 |  | Post | Plan | 2019-08-01 | 2019-08-15 | 2019-08-22 | 2019-09-05 | 2019-09-19 | 2019-10-03 | Plan | 2019-10-10 | 2019-11-09 | 2019-11-30 | 2019-12-14 | 2019-12-21 | 2019-12-28 | 2020-01-11 | Plan | 2020-01-18 | 2020-02-01 |  | 2020-02-08 | 2020-02-22 |  | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
37 | Consultancy Services to conduct Feasibility Studies on rural development infrastructure in Uganda, Niger and Cape Verde | 15/NPCA/NRG/AFRIM/QCBS/2019 | NRG | KFW | QCBS | lumpsum | 102600 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
38 | Consultancy Services for the Knowledge and technical guidelines on AFIRM | 16/NPCA/NRG/AFRIM/IC/2019 | NRG | KFW | ICS | lumpsum | 25000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
39 | Procurement of an Individual Consultant to conduct Capacity Development training on AFRIM in Uganda | 17/NPCA/NRG/AFRIM/IC/2019 | NRG | MSC | ICS | lumpsum | 12000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
40 | Procurement of an Individual Consultant to conduct Capacity Development training on AFRIM in Niger | 17/NPCA/NRG/AFRIM/IC/2019 | NRG | MSC | ICS | lumpsum | 12000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
41 | Procurement of an Individual Consultant to conduct Capacity Development training on AFRIM in Cape Verde | 17/NPCA/NRG/AFRIM/IC/2019 | NRG | MSC | ICS | lumpsum | 12000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
42 | Procurement of an Individual Consultant to Coordinate AFIRM Processes in Uganda | 17/NPCA/NRG/AFRIM/IC/2019 | NRG | MSC | ICS | lumpsum | 9000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
43 | Procurement of an Individual Consultant to Coordinate AFIRM Processes in Niger | 17/NPCA/NRG/AFRIM/IC/2019 | NRG | MSC | ICS | lumpsum | 9000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
44 | Procurement of an Individual Consultant to Coordinate AFIRM Processes in Cape Verde | 17/NPCA/NRG/AFRIM/IC/2019 | NRG | MSC | ICS | lumpsum | 9000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
45 | Procurement of Consultancy services for the Assessment of NEPAD internal Accounting systems and internal control | 16/NPCA/NRG/AFRIM/CQS/2019 | NRG | KFW | CQS | lumpsum | 22000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
46 | Consultancy Services for the AFRIM Audit | 16/NPCA/NRG/AFRIM/CQS/2019 | NRG | KFW | LCS | lumpsum | 9120 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
47 | Consultancy Services to Support Cameroon Gender Ministry with coordination, IMS, policy Review, Gender Mainstreaming tools, communication and M&E | 16/NPCA/NRG/GCCASP/IC/2019 | NRG | NORAD | ICS | lumpsum | 27500 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
48 | Consultancy Service to Support Rwanda Gender Ministry with coordination, IMS, policy Review, Gender Mainstreaming tools, communication and M&E | 6/NPCA/NRG/GCCASP/IC/2019 | NRG | NORAD | ICS | lumpsum | 35778 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
48 | Consultancy Services to Support the Development of Proposals for GCCASP Funding | 16/NPCA/NRG/GCCASP/IC/2019 | NRG | NORAD | ICS | lumpsum | 10000 |  | Prior | Plan | [6 empty] | Plan | [7 empty] | Plan | [7 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
49 | Consultancy Services to develop AUDA-NEPAD Blue Economy Strategy and Action Plan | 6/NPCA/NRG/BE/IC/2019 | NRG | MSC | ICS | lumpsum | 35000 |  | Prior | Plan | [6 empty] | Plan | 2019-04-01 | 2019-04-15 | 2019-04-22 | 2019-05-06 | 2019-05-20 | 2019-06-03 | Plan | 2019-06-10 | 2019-07-10 | 2019-07-31 | 2019-08-14 | 2019-08-21 | 2019-08-28 | 2019-09-11 | Plan | 2019-09-18 | 2019-10-02 |  | 2019-10-09 | 2019-10-23
[10 empty] | Actual | [6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual
50 | Consultancy services to develop policy briefs on extractive industries | 32/NPCA/NRG/EIP/IC/2019 | NRG | MSC | ICS | lumpsum | 20000 |  | Prior | Plan | [6 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | 2019-05-01 | 2019-05-15 | 2019-05-22 | 2019-06-05 | 2019-06-19 | 2019-07-03 | Plan | 2019-07-10 | 2019-08-09 | 2019-08-30 | 2019-09-13 | 2019-09-20 | 2019-09-27 | 2019-10-11 | Plan | 2019-10-18 | 2019-11-01 |  | 2019-11-08 | 2019-11-22
[24 empty] | Actual | [7 empty] | Actual
51 | Consultancy Services to assess Countries diagnostics on extractive decision value chain | 33/NPCA/NRG/EIP/QCBS/2019 | NRG | MSC | QCBS | lumpsum | 80000 |  | Prior | Plan | [6 empty] | Plan
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
52 | Consultancy Services to pilot the menu planner tool in 10 countries | 01/NPCA/NRG/NUTR/IC/2019 | NRG | MSC | ICS | Lumpsum | 10000 |  | Prior | Plan | 2019-04-10 | 2019-04-24 | 2019-05-01 | 2019-05-15 | 2019-05-29 | 2019-06-12 | Plan | 2019-06-19 | 2019-07-19 | 2019-08-09 | 2019-08-23 | 2019-08-30 | 2019-09-06 | 2019-09-20 | Plan | 2019-09-27 | 2019-10-11 |  | 2019-10-18 | 2019-11-01 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
53 | Consultancy Services to develop continental HGSF policy guidelines | 02/NPCA/NRG/NUTR/IC/2019 | NRG | MSC | ICS | Lumpsum | 9000 |  | Prior | Plan | 2019-04-10 | 2019-04-24 | 2019-05-01 | 2019-05-15 | 2019-05-29 | 2019-06-12 | Plan | 2019-06-19 | 2019-07-19 | 2019-08-09 | 2019-08-23 | 2019-08-30 | 2019-09-06 | 2019-09-20 | Plan | 2019-09-27 | 2019-10-11 |  | 2019-10-18 | 2019-11-01 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
54 | Consultancy Services to develop food Composition Tables | 04/NPCA/NRG/NUTR/IC/2019 | NRG | MSC | ICS | Lumpsum | 9000 |  | Prior | Plan | 2019-04-15 | 2019-04-29 | 2019-05-06 | 2019-05-20 | 2019-06-03 | 2019-06-17 | Plan | 2019-06-24 | 2019-07-24 | 2019-08-14 | 2019-08-28 | 2019-09-04 | 2019-09-11 | 2019-09-25 | Plan | 2019-10-02 | 2019-10-16 |  | 2019-10-23 | 2019-11-06 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
55 | Consultancy Services to develop Africa Food Safety Alert Portal / System | 05/NPCA/NRG/NUTR/CQS/2019 | NRG | MSC | SSS | Lumpsum | 30000 |  | Prior | Plan | 2019-04-20 | 2019-05-04 | 2019-05-11 | 2019-05-25 | 2019-06-08 | 2019-06-22 | Plan | 2019-06-29 | 2019-07-29 | 2019-08-19 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-30 | Plan | 2019-10-07 | 2019-10-21 |  | 2019-10-28 | 2019-11-11 |  | Plan | N/A
[10 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
[6 empty] | Total Planned Cost | 4320398 |  |  | Plan
[6 empty] | Total Actual Cost | 0 | 607836.98 |  | Actual | [6 empty] | Actual | [7 empty] | Actual | [7 empty] | Actual
[6 empty] | Total Number of Activities Planned | 68
[6 empty] | Total Number of Activities Implemented | 3
[6 empty] | Number of Activities in Process | 9
Summary
[6 empty] | Department | Plan | Actual | Variance
[6 empty] | BS | 150000 | 0 | 150000
[6 empty] | ISTI | 724400 | 82150 | 642250
[6 empty] | NRG | 1569998 | 0 | 1569998
[6 empty] | OCEO | 456000 | 525686.98 | -69686.98
[6 empty] | RIITP | 942000 | 0 | 942000
[6 empty] | SEFY | 285000 | 0 | 285000
[6 empty] | PIO | 193000 | 0 | 193000
[6 empty] | Total value | 4320398 | 607836.98 | 3712561.02
| Department | Consultancy | Goods | Works | Total by dept
| BS | 150000 | 1197416.17 | 1000000 | 2347416.17
| ISTI | 724400 | 170500 | 800000 | 1694900
| NRG | 1569998 | 239150 | 0 | 1809148
| OCEO | 456000 | 96000 | 0 | 552000
| RIITP | 942000 | 0 | 0 | 942000
| YOUTH & SKILLS | 285000 | 25000 | 0 | 310000
| PIO | 193000 | 73000 | 0 | 266000
| Total value by Category | 4320398 | 1801066.17 | 1800000
7921464.17
| DEPARTMENT | Planned | Actual | %
| Consultancy |  |  | #DIV/0!
| Goods |  |  | #DIV/0!
| Works |  |  | #DIV/0!
| Total Value Category. | 0 | 0 | #DIV/0!
Procurement Executed
Procurement Unexecuted
Formulas:
No-objection Date = [Preparation Terms of Reference]+14
No-objection Date = [Short List]+14
On-line UNDB Gateway/AU WebS. Nat Press = [No-objection Date]+7
On-line UNDB Gateway/AU WebS. Nat Press = [Preparation Terms of Reference]+7
Lead-time before shortlist = [On-line UNDB Gateway/AU WebS. Nat Press]+14
Lead-time before shortlist = [No-objection Date]+7
Short List = [Lead-time before shortlist]+14
Short List = [On-line UNDB Gateway/AU WebS. Nat Press]+14
Request for Proposals = [No-objection Date]+7
Request for Proposals = [Short List]+7
Submission/ Opening Date = [Request for Proposals]+30
Submission Evaluation Report (T) = [Submission/ Opening Date]+21
No-objection Evaluation Report (T) = [Submission Evaluation Report (T)]+14
Opening Financial Proposals = [No-objection Evaluation Report (T)]+7
Negotiations (N) = [Lead-time before shortlist]+14
Draft Contract = [Negotiations (N)]+7
Draft Contract = [Plan vs. Actual]+30
Contract Award = [No-objection Date]+7
Contract Award = [Negotiations (N)]+6
Contract Signature = [Contract Award]+14
Contract Implementation = [Contract Signature]+331
Contract Implementation = [Plan vs. Actual]+14
Draft Report/ Commencment = [Contract Implementation]+26
Plan vs. Actual = [PO Number]+7
Contract Finalization = [No-objection Date]+14
PO Number = [Contract Signature]+14
Final Report = [Contract Implementation]+7
Final Cost = [Final Report]+14
Note on B185: Batho Maruping: description not clear - do what with knowledge products
Note on B188: Batho Maruping: which audit? Financial/performance?
Note on B191: Batho Maruping: re-phrase, not clear. Elaborate?
Note on B194: Batho Maruping: not clear what do u want the consultant to do?
Note on B218: Batho Maruping: Financial Audit or peformance Audit?? Which year FY??
Note on B224: Batho Maruping: can we not combine with Camerron consultancy??
Note on B227: Batho Maruping: which proposal? For Which program?
Note on B236: Batho Maruping: which countries?
Note on E36: Batho Maruping: PIDA CAP project closes Nov 2019
Note on I42: Batho Maruping: Euro 440,000

## Works
ANNUAL 2018 PROCUREMENT PLAN
1 | General
| Organisation: | NEPAD Planning and Coordinating Agency
| Category | WORKS
Project/Programme Description
Project ID
Implementing Unit:
| Approval Date of Procurement Plan: | [Original: ] Revision 1:
| Period Covered by these Proc. Plans: | JAN 2019 - DEC 2019
| Approval Thresholds: | As per AU Procurement Manual
Contract Value
| Selectiont Method | Threshold |  |  | Comments
(USD)
| RFP/RFB | >100,000 |  |  | AUC-IPC Approval
| RFQ/RFB/RFP | 2,001 - 100,000 |  |  | 0-15,000 (Approval by Head of Procurement/Director/Acting Director or OIC) 15,001 - 50,000 (Approval by CEO) 50,0001 - 100,000 (Approval by IPC)
| Direct Selection/RFQ | > 2,000
| Direct Selection/RFQ | ≤2,000 |  |  | non-competitive/RFQ (Approval by Head of Procurement)
Draft Bid Documents, including specs and quantities, draft SPN
[5 empty] | BASIC DATA | [9 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
| Goods contract Procurement Description* | Package Number | Department | Source of Funding | Lot Number | Estimated Amount in US $ | Actual Amount in US $ | Variance | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$'000 | Date Contract Award | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
| Norm Duration of Proc Steps | [10 empty] | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk | 1.5-3 wks
[12 empty] | Actual | [7 empty] | Actual
List of Contracts
1 | Renovation of a primary health care facility in the Eastern Cape |  | ISTI | China Aid | 1 | 800000 |  |  | RFB | Post | Prior | Plan | [7 empty] | Plan
[12 empty] | Actual | [7 empty] | Actual
1 | Renovation works to NEPAD Auditorium, conference room and canteen |  | BS | MSC |  | 1000000 |  |  | RFB | Post | Prior | Plan | [7 empty] | Plan
[12 empty] | Actual | [7 empty] | Actual
2 | [9 empty] | Post | Prior | Plan | [7 empty] | Plan
[12 empty] | Actual | [7 empty] | Actual
4
| Total Cost |  |  |  | Total Planned Cost | 1800000 | [5 empty] | Plan | [7 empty] | Plan | 0
[5 empty] | Total Actual Cost | 0 | 0 |  |  |  |  | Actual | [7 empty] | Actual
[5 empty] | Total Number of Activities Planned |  | 2
[5 empty] | Total Number of Activities Implemented |  | 0
Summary
[5 empty] | Department | Plan | Actual | Variance
[5 empty] | BS | 1000000 | 0 | 1000000
[5 empty] | ISTI | 800000 | 0 | 800000
[5 empty] | NRG | 0 | 0 | 0
[5 empty] | OCEO | 0 | 0 | 0
[5 empty] | RIITP | 0 | 0 | 0
[5 empty] | Youth & Skills | 0 | 0 | 0
[5 empty] | PIO | 0 | 0 | 0
[6 empty] | 1800000 | 0 | 1800000

## Goods
PROCUREMENT PLAN
1 | General
| Organisation: | NEPAD Planning and Coordinating Agency | NEPAD Planning and Coordinating Agency
| Category | GOODS
Project/Programme Description
Project ID
Implementing Unit:
| Approval Date of Procurement Plan: | [Original: ] Revision 1:
| Period Covered by these Proc. Plans: | JAN 2018 - DEC 2018 | JAN 2019 - DEC 2019
| Approval Thresholds: | As per AU Procurement Manual
Contract Value
| Selectiont Method | Threshold |  | Comments
(USD)
| RFP/RFB | >100,000 |  | AUC-IPC Approval
| RFQ/RFB/RFP | 2,001 - 100,000 |  | 0-15,000 (Approval by Head of Procurement/Director/Acting Director or OIC) 15,001 - 50,000 (Approval by CEO) 50,0001 - 100,000 (Approval by IPC)
| Direct Selection/RFQ | > 2,000
| Direct Selection/RFQ | ≤2,000 |  | non-competitive/RFQ (Approval by Head of Procurement)
Draft Bid Documents, including specs and quantities, draft SPN
|  |  |  | BASIC DATA | [9 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization | [5 empty] | Contract Implementation
| Goods contract Procurement Description* | Package Number | Department | Lot Number | Estimated Amount in US $ | Actual Amount in US $ | Variance | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$'000 | Date Contract Award | Date Contract Signature | PO number | BUYER | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
| Norm Duration of Proc Steps | [9 empty] | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk
[11 empty] | Actual | [7 empty] | Actual
List of Contracts
CARRIED OVER FROM 2018
1 | Prequalification tender for the supply, installation and commencement of BIAWE entrepreneurship equipment to four (4) BIAWE incubation centres in four Countries | 03/NPCA/CEO/GD-BIAWE/PQ/2018 | OCEO | 4 | 212000 |  |  | Pre-Qualification (Open) | Pre | Prior | Plan | 2018-04-01 | 2018-04-15 | 2018-04-22 | 2018-04-22 | 2018-06-03 | 2018-06-24 | 2018-07-08 | Plan |  | 2018-07-15 | 2018-07-29 |  | N/A
[11 empty] | Actual | 2018-04-02 | N/A | 2018-04-16 | 2018-04-16 | 2018-05-18 | Changed to Selective Tendering |  | Actual | Changed to Selective Tendering
2 | Prequalification tender for the supply, installation and commencement of BIAWE entrepreneurship equipment to four (4) BIAWE incubation centres in four Countries | 03/NPCA/CEO/GD-BIAWE/PQ/2018 | OCEO | 4 | 212000 |  |  | Pre-Qualification (Selective) | Pre | Prior | Plan | 2018-06-01 | 2018-06-15 | 2018-06-22 | 2018-06-22 | 2018-07-22 | 2018-08-12 | 2018-08-26 | Plan |  | 2018-09-02 | 2018-09-16 |  | N/A
[11 empty] | Actual | 2018-06-12 | N/A | 2018-06-27 | 2018-06-27 | 2018-08-03 |  |  | Actual
3 | Procurement of virtual datacenter equipment and leasing services | 17/NPCA/CS/ADMIN/ICT/RFB/2018 | BS | 1 | 125000 |  |  | RFB | Post | Prior | Plan | 2018-03-01 | N/A | N/A | 2018-03-08 | 2018-03-22 | 2018-04-05 | 2018-04-12 | Plan |  | 2018-04-19 | 2018-05-03
[11 empty] | Actual | [7 empty] | Actual
NEW ACTITIVITIES FOR 2019
1 | Procurement an ambulance and a minibus for staff/patients for a primary health care facility in Easten Cape |  | ISTI |  | 100000 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
2 | Editing of video footage for the baseline situation on TB & Occupation Health of Safety |  | ISTI |  | 18500 |  |  | RFQ | Pre |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
3 | Procurement of TB project communications materials |  | ISTI |  | 52000 |  |  | RFQ | Pre |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
4 | ASTF: Office equipment and Materials for ASTF |  | SEFY |  | 25000 |  |  | RFQ | Pre |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
5 | Hosting and maintenance Services for Grow Africa website - Contract Renewal for Assyst | 01 | NRG | 01 | 15000 |  |  | DP | Post |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
6 | Renewal of Subscription of various service packages for Grow Africa (Google Business, Monkey survey, Mail Chimp) | 04 | NRG | 04 | 5050 |  |  | DP | Post |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
7 | Procurement of Grow Africa Communication Equipment (2 Cameras) | 1 | NRG | 01 | 1000 |  |  | DP | Pre | Post | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
8 | Procurement of USD Communications Materials | 1 | NRG | 01 | 3000 |  |  | RFQ | Pre | Post | Plan |  | N/A | N/A | 1900-01-06 | 1900-01-16 | 1900-01-19 | 1900-01-21 | Plan | 3000 | 1900-01-23 | 1900-01-25
[11 empty] | Actual | [7 empty] | Actual
9 | Procurement of Printing Services for Communication Documents (Drafting, Designing, Translation and Printing of Communication Documents Services) of Grow Africa Corporate Bronchure for 15 countries | 1 | NRG | 02 | 131100 |  |  | RFB | Post | Post | Plan |  | 1900-01-06 | N/A | 1900-01-13 | 1900-02-12 | 1900-02-26 | 1900-03-05 | Plan | 131100 | 1900-03-12 | 1900-03-19
[11 empty] | Actual | [7 empty] | Actual
10 | Procurement of Media services (Press Release & Interviews for GA) - APO | 01 | NRG | 19 | 15000 |  |  | DP | Post |  | Plan |  | N/A | N/A | 1900-01-04 | 1900-01-14 | 1900-01-19 | 1900-01-21 | Plan | 15000 | 1900-01-26 | 1900-02-02
[11 empty] | Actual | [7 empty] | Actual
11 | Procurement of Goods - Printing of publications, e.g 2018 footprint document, comms strategy, AUDA info sheet and brochure |  | OCEO | 1 | 45000 |  |  | RFQ | Post | Post | Plan |  | 1900-01-13 | 1900-01-20 | 1900-02-03 | 1900-02-17 | 1900-03-03 | Plan | 1900-03-10 | 1900-04-09 | 1900-04-30 | 1900-05-14 | 1900-05-21 | 1900-05-28 | 1900-06-11 | Plan | 1900-06-18
[11 empty] | Actual | [7 empty] | Actual
12 | Procurement of Software licence renewals for CLA and Meltwater and purchasing of design software for Comms unit |  | OCEO | 2 | 4000 |  |  | DP | Post |  | Plan |  | 1900-01-13 | 1900-01-20 | 1900-02-03 | 1900-02-17 | 1900-03-03 | Plan | 1900-03-10 | 1900-04-09 | 1900-04-30 | 1900-05-14 | 1900-05-21 | 1900-05-28 | 1900-06-11 | Plan | 1900-06-18
[11 empty] | Actual | [7 empty] | Actual
13 | Procurement of New cameras, business card printing machine, drones and microphones for Comms unit |  | OCEO | 3 | 7000 |  |  | RFQ | Post |  | Plan |  | 1900-01-13 | 1900-01-20 | 1900-02-03 | 1900-02-17 | 1900-03-03 | Plan | 1900-03-10 | 1900-04-09 | 1900-04-30 | 1900-05-14 | 1900-05-21 | 1900-05-28 | 1900-06-11 | Plan | 1900-06-18
[11 empty] | Actual | [7 empty] | Actual
14 | Procurement of Promotional materials for Comms |  | OCEO | 3 | 40000 |  |  | RFQ | Post |  | Plan |  | 1900-01-13 | 1900-01-20 | 1900-02-03 | 1900-02-17 | 1900-03-03 | Plan | 1900-03-10 | 1900-04-09 | 1900-04-30 | 1900-05-14 | 1900-05-21 | 1900-05-28 | 1900-06-11 | Plan | 1900-06-18
[11 empty] | Actual | [7 empty] | Actual
15 | Procurement of Translation services for the NEPAD portal |  | PIO | 4 | 30000 |  |  | RFQ | Post |  | Plan |  | 1900-01-13 | 1900-01-20 | 1900-02-03 | 1900-02-17 | 1900-03-03 | Plan | 1900-03-10 | 1900-04-09 | 1900-04-30 | 1900-05-14 | 1900-05-21 | 1900-05-28 | 1900-06-11 | Plan | 1900-06-18
[11 empty] | Actual | [7 empty] | Actual
16 | Procurement of exhibition equipment for the launch of the NEPAD portal |  | PIO | 5 | 20000 |  |  | RFQ | Post |  | Plan |  | 1900-01-13 | 1900-01-20 | 1900-02-03 | 1900-02-17 | 1900-03-03 | Plan | 1900-03-10 | 1900-04-09 | 1900-04-30 | 1900-05-14 | 1900-05-21 | 1900-05-28 | 1900-06-11 | Plan | 1900-06-18
[11 empty] | Actual | [7 empty] | Actual
17 | Procurement of software licences for the NEPAD web-portal |  | PIO | 6 | 13000 |  |  | DP | Post |  | Plan |  | 1900-01-13 | 1900-01-20 | 1900-02-03 | 1900-02-17 | 1900-03-03 | Plan | 1900-03-10 | 1900-04-09 | 1900-04-30 | 1900-05-14 | 1900-05-21 | 1900-05-28 | 1900-06-11 | Plan | 1900-06-18
[11 empty] | Actual | [7 empty] | Actual
18 | Procurement of web-content, including knowledge products for SKM (Design and Layout and Printing of Knowledge products) |  | PIO | 6 | 10000 |  |  | RFQ | Post |  | Plan |  | 1900-01-13 | 1900-01-20 | 1900-02-03 | 1900-02-17 | 1900-03-03 | Plan | 1900-03-10 | 1900-04-09 | 1900-04-30 | 1900-05-14 | 1900-05-21 | 1900-05-28 | 1900-06-11 | Plan | 1900-06-18
[11 empty] | Actual | [7 empty] | Actual
19 | Procurement of office equipment and licences for Admin Unit |  | BS |  | 10000 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan | 10000
[11 empty] | Actual | [7 empty] | Actual
20 | Procurement of Network/Computer equipment and configuration (Hardware, Software and Service) |  | BS |  | 146000 |  |  | RFB | Post |  | Plan | [7 empty] | Plan | 146000
[11 empty] | Actual | [7 empty] | Actual
21 | Procurement of ICT Operation Center equipment, software and accessories |  | BS |  | 90000 |  |  | RFB | Post |  | Plan | [7 empty] | Plan | 146000
[11 empty] | Actual | [7 empty] | Actual
22 | Procurement of IT Training on Network, Security and Service Provision system |  | BS |  | 80000 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan | 146000
[11 empty] | Actual | [7 empty] | Actual
23 | Procurement of mobile phone Contracts and 3G services |  | BS |  | 150000 |  |  | DP | Pre |  | Plan | [7 empty] | Plan | 150000
[11 empty] | Actual | [7 empty] | Actual
24 | Procurement of office consumables, groceries, kitchen appliances and stationery etc) |  | BS |  | 35000 |  |  | RFQ | Pre |  | Plan | [7 empty] | Plan | 12344.59
[11 empty] | Actual | [7 empty] | Actual
25 | Procurement of security services for NEPAD offices |  | BS |  | 115035 |  |  | RFB | Post |  | Plan | [7 empty] | Plan | 115035
[11 empty] | Actual | [7 empty] | Actual
26 | Maintenance, supervision and Evaluation of cleaning services for NEPAD offices |  | BS |  | 69781.02 |  |  | RFB | Post |  | Plan | [7 empty] | Plan | 69781.02
[11 empty] | Actual | [7 empty] | Actual
27 | Procurement of security system enhancements equipment |  | BS |  | 15000 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan | 15000
[11 empty] | Actual | [7 empty] | Actual
28 | Procument of delivery of newspapers to NEPAD office |  | BS |  | 12534.15 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan | 12534.15
[11 empty] | Actual | [7 empty] | Actual
29 | Procurement of water and milk for NEPAD office |  | BS |  | 9930 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan | 9930
[11 empty] | Actual | [7 empty] | Actual
30 | Leasing of additional office space(Within and outside the premises) |  | BS |  | 219136 |  |  |  | Post |  | Plan | [7 empty] | Plan | 219136
[11 empty] | Actual | [7 empty] | Actual
31 | Functionalizing of inventory management system |  | BS |  | 5000 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan | 5000
[11 empty] | Actual | [7 empty] | Actual
32 | Procurement of Office Furniture |  | BS |  | 50000 |  |  |  | Post |  | Plan | [7 empty] | Plan | 50000
[11 empty] | Actual | [7 empty] | Actual
33 | Procurement of Laptops and computer accessories |  | BS |  | 70000 |  |  | RFB | Post |  | Plan | [7 empty] | Plan | 70000
[11 empty] | Actual | [7 empty] | Actual
34 | Framework contract for transport services |  | BS |  | 10000 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan | 10000
[11 empty] | Actual | [7 empty] | Actual
35 | Training and Installation of Amadeus for travel unit |  | BS |  | 20000 |  |  | DP | Post |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
36 | Training of IPC members on the new Procurement manual Version 3 |  | BS |  | 20000 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
37 | NEPAD Annual Procurement Plan retreat- 2019 |  | BS |  | 40000 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
38 | Purchase of Mobility Plan IT Software |  | BS |  | 10000 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
39 | Advertisements of Tenders |  | BS |  | 20000 |  |  | RFQ | Post |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
40 | Framework Contract for Video Production services | 04/NPCA/CS/ADMIN/FMC/2018 | BS | 1 | 0 |  |  | RFB | Post | Prior | Plan |  | 1900-01-13 | 1900-01-20 | 1900-01-20 | 1900-02-19 | 1900-03-12 | 1900-03-26 | Plan |  | 1900-04-02 | 1900-04-16 |  | N/A
[11 empty] | Actual | [7 empty] | Actual
41 | Framework Contract for supply of stationery and office supplies | 05/NPCA/CS/ADMIN/FMC/2018 | BS | 2 | 0 |  |  | RFB | Post | Prior | Plan |  | 1900-01-13 | 1900-01-20 | 1900-01-20 | 1900-02-19 | 1900-03-12 | 1900-03-26 | Plan |  | 1900-04-02 | 1900-04-16 |  | N/A
[11 empty] | Actual | [7 empty] | Actual
42 | Framework Contract for Communication & Promotion Materials – Including Branding, Design and printing services | 06/NPCA/CS/ADMIN/FMC/2018 | BS | 4 | 0 |  |  | RFB | Post | Prior | Plan |  | 1900-01-13 | 1900-01-20 | 1900-01-20 | 1900-02-19 | 1900-03-12 | 1900-03-26 | Plan |  | 1900-04-02 | 1900-04-16 |  | N/A
[11 empty] | Actual | [7 empty] | Actual
43 | Framework Contract for provision of transportation services for NEPAD Agency | 07/NPCA/CS/ADMIN/FMC/2018 | BS | 1 | 0 |  |  | RFB | Post | Prior | Plan |  | 1900-01-13 | 1900-01-20 | 1900-01-20 | 1900-02-19 | 1900-03-12 | 1900-03-26 | Plan |  | 1900-04-02 | 1900-04-16 |  | N/A
[11 empty] | Actual | [7 empty] | Actual
44 | Framework Contract for provision of catering services for NEPAD Agency | 08/NPCA/CS/ADMIN/FMC/2018 | BS | 1 | 0 |  |  | RFB | Post | Prior | Plan |  | 1900-01-13 | 1900-01-20 | 1900-01-20 | 1900-02-19 | 1900-03-12 | 1900-03-26 | Plan |  | 1900-04-02 | 1900-04-16 |  | N/A
[11 empty] | Actual | [7 empty] | Actual
45 | GCCASP Knowledge Management Products and Promotional Materials |  | NRG |  | 15000 |  |  |  | Post |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
46 | GCCASP Knowledge Management Portal and Catalogue |  | NRG |  | 30000 |  |  |  | Post |  | Plan | [7 empty] | Plan
[11 empty] | Actual | [7 empty] | Actual
47 | Procurement of Goods - Design and printing of the policy guidelines, harmonised food standards and food composition table |  | NRG | 1 | 24000 |  |  | RFQ | Post | Post | Plan |  | 1900-01-13 | 1900-01-20 | 1900-02-03 | 1900-02-17 | 1900-03-03 | Plan | 1900-03-10 | 1900-04-09 | 1900-04-30 | 1900-05-14 | 1900-05-21 | 1900-05-28 | 1900-06-11 | Plan | 1900-06-18
[11 empty] | Actual | [7 empty] | Actual
| Total Cost |  |  | Total Planned Cost | 1801066.17 | [5 empty] | Plan | [7 empty] | Plan | #REF!
|  |  |  | Total Actual Cost | 0 | 0 |  |  |  |  | Actual | [7 empty] | Actual
|  |  |  | Total Number of Activities Planned |  | 50
|  |  |  | Total Number of Activities Implemented |  | 0
Number of Activities in Process
Summary
|  |  |  | Department | Plan | Actual | Variance
|  |  |  | BS | 1197416.17 | 0 | 1197416.17
|  |  |  | ISTI | 170500 | 0 | 170500
|  |  |  | NRG | 239150 | 0 | 239150
|  |  |  | OCEO | 96000 | 0 | 96000
|  |  |  | RIITP | 0 | 0 | 0
|  |  |  | SEFY | 25000 | 0 | 25000
|  |  |  | PIO | 73000 | 0 | 73000
|  |  |  | TOTAL | 1801066.17 | 0 | 1801066.17
Formulas:
No-objection Date = [Prep & Submission by Ex Agency]+14
No-objection Date = [Bid Evaluation]+14
Spec Proc Notice Advert = [No-objection Date]+7
Spec Proc Notice Advert = [Prep & Submission by Ex Agency]+14
Bidding Period = [Spec Proc Notice Advert]
Bidding Period = [Prep & Submission by Ex Agency]+7
Bid Closing-Opening = [Bidding Period]+42
Bid Closing-Opening = +[Bidding Period]+30
Bid Evaluation = [Bid Closing-Opening]+21
Date Contract Award = [No-objection Date]+7
Date Contract Award = [Contract Finalization]+21
Date Contract Signature = [Date Contract Award]+14
Plan vs. Actual = [Bid Evaluation]+7
Contract Finalization = [Plan vs. Actual]+30
PO number = [Date Contract Signature]+7
BUYER = [PO number]+7
Opening of Let of Credit = [BUYER]+14
Inspection Final Acceptance = [Opening of Let of Credit]+7

## Sheet1
Consultancy | 5399900
Goods | 1472790
Works | 235000
Meetings & Conference | 649515.65
7757205.65
NRG | 3039850
OCEO | 1442745.75
BS | 905240
RIIT | 780595
ISTI | 491100
YOURTH & SKILLS | 121000
Total Value | 6780530.75
NRG | 3039850
OCEO | 1442745.75
BS | 905240
RIIT | 780595
ISTI | 491100
YOURTH & SKILLS | 121000

## list of promotional materials
LIST OF PROMOTIONAL MATERIALS
BASIC DATA
| Goods contract Procurement Description* | Business Unit | Source of Funds | Estimated Amount in US $ | Actual Amount in US $ | Supplier | PO Number | BUYER
List of Contracts
1 | Produce and disseminate quarerly newsletters in English and French - STEM | ISTI | MS | 8000
2 | Design print and disseminate training materials and STEM/STI resources to inform policy | ISTI | MS | 12000
3 | Printing SGCI synthesized reports, pamphlets and policy briefs, AIO3. ASTII | ISTI | ISSGC103223???? | 27500
4 | Production and printing of Guiding documents (policy briefs) for STI champions and status of health research and innovation - AESA | ISTI | DP??? | 30000
5 | Design, print and disemminate the Clinical Trails Training Manual - AMRH | ISTI | USAID/MSH MTaPs | 20000 | x
#REF! | Produce and disseminate a popular version of AMRH annual report sumamry | ISTI | BMGF | 5000 | x
#REF! | Produce and dissemiante AMRH advocacy materials i.e. videos, policy briefs, infograpghics, podcasts, etc. | ISTI | BMGF | 14000 | X
#REF! | Publish AMRH articles and success stories in the media | ISTI | BMGF | 8000 | x
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
|  |  | Estimated Total | 124500
Total Number of Activities Planned
Total Number of Activities Implemented

## Meetings
DOCUMENT SUBMISSION WITHIN PROCUREMENT UNIT
DATE | SUPPLIER NAME | SERVICE DESCRITION | PO NUMBER | PO DATE | FUNDER | REQUESTING UNIT | ZAR AMOUNT | USD AMOUNT | CORINE | ASEYE | COMMENTS

## list of VIDEO productions
LIST OF VIDEO PRODUCTIONS
BASIC DATA
| Goods contract Procurement Description* | Business Unit | Source of Funds | Estimated Amount in US $ | Actual Amount in US $ | Vendor | Contract Signature | PO Number | BUYER
List of Contracts
1
2
3
4
5
6
7
8
| Total Cost |  | Total Planned Cost | 0
|  |  | Total Actual Cost |  | 0
|  |  | Total Number of Activities Planned |  | 7
Total Number of Activities Implemented
Summary
|  |  | Department | Plan | Actual
BS
ISTI
NRG
OCEO
RIIT
Youth & Skills

## TR
2019-01-01
DOCUMENT SUBMISSION WITHIN PROCUREMENT UNIT
DATE | SUPPLIER NAME | SERVICE DESCRITION | TR NUMBER | TR DATE | WBS | REQUESTING UNIT | ZAR AMOUNT | USD AMOUNT | CORINE | ASEYE | COMMENTS

## Sheet2
Description | Amount
Planning
Planned Procurement Activities | 7921464.17
Actual Cost
Implemented planned Procurement Activities | 607836.98 | 29
Implemented Meetings/Workshops | #REF!
Tickets
Contracts Extension
Subtotal | #REF!
Variance
Description | Amount
Planning
Planned Procurement Activities | 0
Actual Cost
Implemented planned Procurement Activities | 0 | 29
Implemented Meetings/Workshops | #REF!
Tickets
Subtotal | #REF!
Variance